From                                                                  		            To

Smt. P.Anuradha,                              			            All the Project Directors

Mission Director (FAC)                             		            Telangana

MEPMA, Telangana

Circular. No. 455/SUH/D/2014, date:  15 -10-2014

Sub:  	MEPMA–NULM- Completion of activities of Shelter for Urban Homeless – Urgent - Instructions- Issued.

Ref: - 1.This office circular Rc. No.  MEPMA/455/SUH/D1/2014 dated 05-08-2014

2. Supreme Court of India order on WP 55/2003 & WP 572/2003 dated

09-09-2014

<><><>

All the Project Directors were directed to conduct survey for indentifying urban homeless in NULM towns, identify the suitable building for shelter, select the NGO/CBO to maintain the shelter, constitute a committee for overall monitoring of the programme and submit the Detailed Project Report (DPR) for approval, through ref. 1st cited.

The Hon’ble Supreme Court of India has ordered for submission of affidavit on the action taken and also the time frame within which the scheme shall be made fully operation in the state, vide ref. 2nd cited.

As the progress is very slow in the districts, the following are the activities to be taken up by the DPMUs on priority.

- Survey to identify the beneficiaries

- Categorization of the registered beneficiaries

- Submitting the data of registered candidates to this office (hard &soft copies)

- Uploading the beneficiary data in the portal - http://www.tmepma.cgg.gov.in

- Identification of suitable building

- Refurbishment of the building

- Identification of NGO/CBO to maintain the Shelter through bidding process.

- Submit the Detailed Project Report (DPR)  with all administrative and regulatory clearances e.g. Building fitness certificate

- Constituting a Shelter Management committee (SMC)

- Starting the operations of the Shelter.

Hence all the Project Directors are hereby directed to expedite the process and complete the task of establishing and running the centers by 15-11-2014 without fail. The time frame is enclosed herewith and should strictly follow without fail. Any deviation/delay in this regard would be viewed seriously and action would be taken against the concerned.

Sd/- P.Anuradha

MISSION DIRECTOR (FAC)

Time Frame to establish the Shelters

| S. No | Activity | Time Frame given vide Rc. No. MEPMA/455/SUH/D1/2014 dated 05-08-2014 | Present Status | Performance of PDs | To be completed by date |
| --- | --- | --- | --- | --- | --- |
| 1 | Survey to identify the beneficiaries | 21.08.2014 | Pending at Nalgonda, Miryalaguda, Sangareddy | Poor | 16th Oct |
| 2 | Categorization of the registered beneficiaries | 21.08.2014 | Pending at Nalgonda, Miryalaguda, Sangareddy | Poor | 17th Oct |
| 3 | Submitting the data of registered candidates to head office (hard & soft copies) | 22.08.2014 | Pending at Nalgonda, Miryalaguda, Sangareddy | Poor | 18th Oct |
| 4 | Uploading the beneficiary data in the portal - http://www.tmepma.cgg.gov.in | 22.08.2014 | Pending at Karimnagar, Jagityal, Ramagundam, Sangareddy | Poor | 18th Oct |
| 5 | Identification of suitable building |  | Except Mahabubnagar, Suryapeta, Adilabad remaining are pending | Poor | 20th Oct |
| 6 | Identification of NGO/CBO to maintain the Shelter through bidding process. |  | Except Mahabubnagar, remaining are pending | Poor | 21st Oct |
| 7 | Submit the Detailed Project Report (DPR) with all administrative and regulatory clearances e.g. Building fitness certificate & budget. | 27.08.2014 | Pending at all NULM Towns | Poor | 25th Oct |
| 8 | Refurbishment of the building |  |  |  | 5th Nov |
| 9 | Constituting a Shelter Management committee (SMC) |  |  |  | 5th Nov |
| 10 | Starting the operations of the Shelter |  |  |  | 15th Nov |

******